Name Team 9

Members Jairo Galarza, Alex Lundin, Brenden Pace, Daniel Park

Class SE 4381.501 Project Management

Assignment Team Assignment #3

Work Breakdown Structure

|  |  |  |  |
| --- | --- | --- | --- |
| Level 1 | Level 2 | Level 3 Work Packages | Level 4 Estimations |
| 1 Overview of ISO/IEC/IEEE 12207 | 1.1 WBS | 1.1.1 Group Meeting and Starting Template | 3 hours |
| 1.1.2 Identify Main Objectives | 2 hours |
| 1.1.3 Create Sub-Objects and Complete Table | 3 hours |
| 1.1.4 Select Research Documents | 1 hour |
| 1.2 Project Plan | 1.2.1 Organize Objectives | 3 hours |
| 1.2.2 Distribute objectives amongst team members | 2 hours |
| 1.3 Research and Summarize | 1.3.1 Research and Identify Sources | 2 hours |
| 1.3.2 Split Sources and Read | 8 hours |
| 1.3.3 Create Outline for Research Paper Content | 1 hour |
| 1.3.4 Summarize Our Research | 4 hours |
| 1.4 Document Observations | 1.4.1 Split Research into Subtopics | 3 hours |
| 1.4.2 Categorize Information and Quotes into the Split Subtopics | 2 hours |
| 1.5 Write Report | 1.5.1 Group Meeting and Create Report Outline based on Research | 2 hours |
| 1.5.2 Create a first Draft of the report based on Research | 4 hours |
| 1.5.3 Revise Report Draft and Report Outline | 2 hours |
| 1.5.4 Finalize report | 3 hours |
| 1.6 Write Presentation | 1.6.1 Create Presentation Outline Based on Report | 1 hours |
| 1.6.2 Complete Presentation Slides | 3 hours |
| 1.6.3 Revise Slides | 1 hour |
| 1.6.4 Finalize Slides, Create Notes, and Give Presentation | 2 hours |
| 1.7 Lessons Learned | 1.7.1 Create Summary on Mistakes that were made | 1 hour |
| 1.7.2 Discuss Alternatives That Could Have Been Made | 1 hour |
| 1.8 Individual Ratings and Group Performance | 1.8.1 Evaluate performance of Teammates | 1 hour |
| 1.8.2 Evaluate performance of group | 1 hour |