## Sheet1
Traditional | [5 empty] | Agile
Level 1 | Level2 | Level 3 | Level 4 | Level 6 | Level 7 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5
Milestone Name | Categories | Work Packages | Estimations | Actual | Status | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05
Wireless Additions | Floor Plan | Create linetype | 0.1 | 0.3 | 1 |  |  | 0.3
|  | Print Example pdf | 0.1 | 0.3 | 1 |  |  | 0.3
| Riser | Restructure - wireless bridge on vertical rung | 1 | 1 | 1 |  |  |  |  | 1
|  | Restrucutre - add additional wireless segement type | 1 | 1 | 1 |  |  |  |  | 1
|  | Restructure- draw viewports around all segments | 1 | 1 | 1 |  |  |  |  | 1
| Room Details | Restructure - group occupancy and interfaces on their own rung | 1 | 1 | 1 |  |  |  |  | 1
|  | Restructure - 2 rungs from the Bridge | 4.5 | 4.5 | 1 | [6 empty] | 4.5
|  | Restructure - tighten all coordinate shifts | 4.5 | 4.5 | 1 | [6 empty] | 4.5
|  | Restrucutre - add wireless controller rung | 2 | 1 | 1 | [11 empty] | 1
|  | Restrucutre - add wireless device rung | 2 | 1 | 0 | [11 empty] | 1
| Relative Paths | Addition - String Constants File | 2 | 4.5 | 1 | 4.5
|  | Restructure- legacy code | 2 | 4.5 | 1 |  | 4.5
|  | Restructure- library code | 2 | 2 | 1 | [9 empty] | 2
|  | Restrucutre - callable functions | 2 | 2 | 1 | [9 empty] | 2
| Testing and Release | Unit Tests, Regression Tests, Test Cases | 3 | 0 | 0
|  | Document Test Profile Usage | 1 | 0 | 0
|  | Install Alpha (first release) for 3 engineers | 1.5 | 0 | 0
|  | Beta (second release) for 9 engineers | 3 | 0 | 0
|  | Golden Copy (live environment code) release steps for all | 3 | 0 | 0
| Recofigurations Between Release | Submittal 2.0 | 3 | 2 | 0 | [9 empty] | 1 |  | 1
|  | Alpha | 3 | 0 | 0
|  | Beta | 1.5 | 0 | 0
|  | Golden Copy | 0 | 0 | 0
| Planning | Create Burndown from Existing Data | 2 | 2 | 1 | [8 empty] | 2
|  | Continue to log | 1 | 0 | 0
|  | Total Days |  |  | 15
|  | Ideal Task Burndown |  |  | 25 | 23.3333 | 21.6667 | 20 | 18.3333 | 16.6667 | 15 | 13.3333 | 11.6667 | 10 | 8.3333 | 6.6667 | 5 | 3.3333 | 1.6667 | -3.9968e-15
|  | Tasks Remaining |  |  | 14
|  | Logged Effot |  |  |  | 4.5 | 4.5 | 0.6 | 0 | 4 | 0 | 9 | 0 | 2 | 5 | 0 | 3 | 0 | 0 | 0
|  | Remaining Effort | 47.2 |  |  | 42.7 | 38.2 | 37.6 | 37.6 | 33.6 | 33.6 | 24.6 | 24.6 | 22.6 | 17.6 | 17.6 | 14.6 | 14.6 | 14.6 | 14.6
|  | Ideal Effort Burndown | 47.2 |  |  | 44.0533 | 40.9067 | 37.76 | 34.6133 | 31.4667 | 28.32 | 25.1733 | 22.0267 | 18.88 | 15.7333 | 12.5867 | 9.44 | 6.2933 | 3.1467 | -1.1546e-14