## Slide 1: London Stock Exchange
Presented by: Patrick Hale, Adam Goodman, Akib Hossain, Alexander Lundin
Notes: Patrick - start and
Each group member introduces themselves, in order of the names presented, then goes over the title and what will be presented

## Slide 2: History
The LSE commissioned a project to automate and transfer stocks.
Taurus - Transfer and Automated Registration of Uncertified Stock.
Goals
  increase LSE cost efficiency
  by decreasing face to face meeting
“big bang” in 1986
  LSE became self-regulating
  only answering to the Bank of England.
LSE wanted to emulate the New York Stock Exchange.
Notes: Patrick
The London Stock Exchange commissioned a project to automate and transfer stocks.
Taurus stands for Transfer and Automated Registration of Uncertified Stock, goal to make the LSE more cost efficient and decreasing the time commitment by not needing to have face to face meeting.
The contributing factor to Taurus being developed was what's known as the “big bang” in 1986 which was when the London Stock Exchange was turned into a self-regulating organization only answering to the Bank of England.
The London Stock Exchange wanted to emulate the New York Stock Exchange.

## Slide 3: The Problems
1. Lack of comprehension.
2. Utilizing Vista
3. Unable to stabilize requirements
Notes: Alex

## Slide 4: Problem One, Lack of Comprehension: Management Incompetence
Contributing Factors:
New management in big businesses
Long transaction time
Resulting Mindset, Decisions and Outcome
Sheer Blind Panic
Cut paper system
Organizational dysfunction was the cause [1]
Intermediate Thoughts
Antiquated system is cause [1]
Electronic system will decrease time [1]
This will increase profits
[2]
Notes: Alex
Factors (Transition time was ~ 3 weeks)
Thoughts (The decision to remove the paper system was based on the myth that the inefficiencies embedded in the system reduced profits)
Result (Sheer Blind Panic lead to the decision to cut the paper system[1].)

## Slide 5: Problem Two, Utilizing Vista: Escalation from Logic
Contributing Factors:
Wanted American software packages
Different economic laws and practices in comparison to US.
Lead to decision of Vista use [1]
Intermediate Thoughts
off the shelf would speed up delivery.
proven track record of off the shelf [1]
LSE didn’t have the means to take care of the issue itself [1]
Resulting Mindset, Decisions and Outcome
Escalation from Logic[1]
disgruntled project members[1]
60% rewrite of vista in order to comply[4]
Result, multiple bugs & increased delivery time[1]
conversion vastly exceeded budget [1]
[3]
Notes: Alex
Factors (Bill Widdis was the project leader and the deciding factor upon purchasing Vista, he based his
Thoughts (LSE weighted the risk involved with off the shelf and decided to proceed regardless, creating work from scratch was beyond their capability) (Bill actually had the rationale of the lack of resource behind his decision)
Result (this all stemmed from Escalation based in Logic, which is strange because Escalation usually starts with foolheartedly[1])(decision to acquire personnel would have been cheaper that the rework)

## Slide 6: Problem Three, Unable to stabilize requirements
Contributing Factors:
Management's goal to maintain commitment to Taurus[1]
construction began before requirements[1]
Resulting Mindset, Decisions and Outcome
Re-code and Re-do
No defined scope for the project
Lead to uncontrolled budget
Communication burden
Intermediate Thoughts
Too many parties involved
Constant requirement change
[5]
Notes: Factors (Management wanted to stay committed to Taurus despite the predicted failure rate) (Also Construction started before requirements to maintain project momentum[1])
Thoughts (Security industry became involved and other boards)
Result (re-code, re-do, the continuous changes made it impossible to define a project scope, due to the iron triangle of Software development, this affected the budget)(all the changes lead to too much communication between users and manufacturues)

## Slide 7: Summary of the Issues
1. Management lacked comprehension, LSE had long transaction times, and new management
2. Vista, disgruntled employees, project still buggy after rework
3. Requirements and scope never reached a static state
Notes: Just a run down of the main points that caused the issues for the london stock exchange project
London’s stock exchange lacked the comprehension needed for the scope of the project, had long transactions, and were under new management
The stock exchange opted to utilize Vista, which displeased members and required numerous fixes to Vista to make it comply, was still buggy after.
The stock exchange proceeded to build the project before the requirements were finalized and led to more work having to change the project as the requirements changed.

## Slide 8: References
[1] H. Drummond, “The politics of risk: trials and tribulations of the Taurus project,” Journal of Information Technology, vol. 11, no. 4, pp. 347–357, 1996.
[2] Google Search. [Online]. Available: https://www.google.com/imgres?imgurl=https://thumbs.dreamstime.com/b/artificial-intelligence-concept-abstract-illustration-electronic-circuit-board-brain-profile-ai-49732960.jpg&imgrefurl=https://www.dreamstime.com/stock-illustration-artificial-intelligence-concept-abstract-illustration-electronic-circuit-board-brain-profile-ai-image49732960&docid=4uSiCCa96XWOJM&tbnid=4xGcNjSwPaZ3MM:&vet=10ahUKEwiJt-THysDbAhUJR6wKHbX_DXcQMwhcKBowGg..i&w=800&h=829&bih=925&biw=1920&q=ai brain concept art&ved=0ahUKEwiJt-THysDbAhUJR6wKHbX_DXcQMwhcKBowGg&iact=mrc&uact=8. [Accessed: 07-Jun-2018].
[3] “Windows Vista - Manual update,” CCM. [Online]. Available: https://ccm.net/faq/2013-windows-vista-manual-update. [Accessed: 07-Jun-2018].
[4] Flowers, Stephen. Software Failure: Management Failure: Amazing Stories and Cautionary Tales. Wiley, 1996.
[5] Y. Essack, “The Iron Triangle Of Management,” ToughNickel, 12-May-2016. [Online]. Ava
ilable: https://toughnickel.com/business/The-Iron-Triangle-Of-Management. [Accessed: 07-Jun-2018].