## Sheet1
Average reader reads 200 WPM and the average chapter is 2500 words. 12 minutes a chapter
Traditional | [5 empty] | Agile
Level 1 | Level2 | Level 3 | Level 4 | Level 6 | Level 7 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5
Milestone Name | Categories | Work Packages | Estimations | Actual | Status | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05
Report | Research | Find CCPM references | 1 | 1 | 1 | 1
|  | Find Traditional Management references | 2 | 2 | 1 | [5 empty] | 1 | 1
| Read references and find key points | Critical Chain | 5 | 3 | 0 |  |  |  |  | 1 |  |  | 1 | 1
|  | A Critical Look at Critical Chain Project Management | 0.2 | 0 | 0
|  | Buffers & Risk Critical Chain Project Management | 1 | 0 | 0
|  | Critical Chain Project Management-A Critique | 0.3 | 0 | 0
|  | Critical Path Method (CPM) | 1 | 0 | 0
|  | Critical Path Versus Critical Chain A Comparative View | 1 | 0 | 0
|  | The Goal | 8 | 0 | 0
| Individual Summaries | Critical Chain | 1.5 | 0.4 | 0 | [6 empty] | 0.2 |  |  | 0.2
|  | A Critical Look at Critical Chain Project Management | 0.1 | 0 | 0
|  | Buffers & Risk Critical Chain Project Management | 0.3 | 0 | 0
|  | Critical Chain Project Management-A Critique | 0.1 | 0 | 0
|  | Critical Path Method (CPM) | 0.3 | 0 | 0
|  | Critical Path Versus Critical Chain A Comparative View | 0.3 | 0 | 0
|  | The Goal | 2.5 | 0 | 0
| Draft | Structure - Introduction, body, conclusion | 4 | 0 | 0
|  | Citations | 1 | 0 | 0
|  | Proof read | 2 | 0 | 0
|  | Peer review | 1 | 0 | 0
| Final Version | Finalize paper | 1 | 0 | 0
|  | Group consensus | 2 | 0 | 0
Presentation | Research | Find diagrams | 2 | 0 | 0
|  | Find references | 1 | 0 | 0
| Draft | 10-15 minutes long = 10 - 15 slides | 3 | 0 | 0
|  | Slides: keep short -> include images |  | 0 | 0
|  | Proof read | 1 | 0 | 0
|  | Peer review | 1 | 0 | 0
| Final Version | Finalize presentation | 1 | 0 | 0
|  | Group consensus | 1 | 0 | 0
|  | Lessons learned | 0.2 | 0 | 0
lessons learned report | Draft | Rate teammates | 0.2 | 0 | 0
|  | summarize contributions of each member | 0.2 | 0 | 0
|  | Targets, to get on track | [9 empty] | 5.9 | 5.9 | 5.9 | 5.9
|  | Total Days |  |  | 15
|  | Ideal Task Burndown |  |  | 33 | 30.8 | 28.6 | 26.4 | 24.2 | 22 | 19.8 | 17.6 | 15.4 | 13.2 | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 7.1054e-15
|  | Tasks Remaining |  |  | 33
|  | Logged Effot | 6.4 |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 1.2 | 1 | 1 | 0.2 | 0 | 0 | 0 | 0 | 0
|  | Remaining Effort | 46.2 |  |  | 45.2 | 45.2 | 45.2 | 45.2 | 44.2 | 43.2 | 42 | 41 | 40 | 39.8 | 39.8 | 39.8 | 39.8 | 39.8 | 39.8
|  | Ideal Effort Burndown | 46.2 |  |  | 43.12 | 40.04 | 36.96 | 33.88 | 30.8 | 27.72 | 24.64 | 21.56 | 18.48 | 15.4 | 12.32 | 9.24 | 6.16 | 3.08 | 6.2172e-15
Agile