## Sheet1
Work Packages | Estimations | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Work Hours
1.1.1 Group Meeting and Starting Template | 3 | [16 empty] | 1 | bar: Week 3
1.1.2 Identify Main Objectives | 2 | Week 3: 2 | 2
1.1.3 Create Sub-Objects and Complete Table | 3 | Week 3: 0.5 | 0.5
1.1.4 Select Research Documents | 1 | [16 empty] | 2 | bar: Week 4; Week 7
1.2.1 Organize Objectives | 3 | Week 4: 0.5 | 0.5
1.2.2 Distribute objectives amongst team members | 2 | Week 5: 0.5 | 0.5
1.3.1 Research and Identify Sources | 2 | Week 6: 2; Week 7: 2 | 4
1.3.2 Split Sources and Read | 8 | Week 8: 1; Week 9: 1; Week 12: 2 | 4
1.3.3 Create Outline for Research Paper Content | 1 | [16 empty] | 0
1.3.4 Summarize Our Research | 4 | Week 10: 3 | 3
1.4.1 Split Research into Subtopics | 3 | Week 11: 0.5 | 0.5
1.4.2 Categorize Information and Quotes into the Split Subtopics | 2 | Week 12: 4 | 4
1.5.1 Group Meeting and Create Report Outline based on Research | 2 | Week 12: 4 | 4
1.5.2 Create a first Draft of the report based on Research | 4 | Week 12: 3 | 3
1.5.3 Revise Report Draft and Report Outline | 2 | [16 empty] | 1 | bar: Week 12
1.5.4 Finalize report | 3 | [16 empty] | 1 | bar: Week 12
1.6.1 Create Presentation Outline Based on Report | 1 | [16 empty] | 0
1.6.2 Complete Presentation Slides | 3 | [16 empty] | 0
1.6.3 Revise Slides | 1 | [16 empty] | 0
1.6.4 Finalize Slides, Create Notes, and Give Presentation | 2 | [16 empty] | 0
1.7.1 Create Summary on Mistakes that were made | 1 | [16 empty] | 0
1.7.2 Discuss Alternatives That Could Have Been Made | 1 | [16 empty] | 0
1.8.1 Evaluate performance of Teammates | 1 | [16 empty] | 0
1.8.2 Evaluate performance of group | 1 | [16 empty] | 0
Work Hours |  | 0 | 0 | 3.5 | 1.5 | 0.5 | 2 | 3 | 1 | 1 | 3 | 0.5 | 15 | 0 | 0 | 0 | 0
Remaining Effort | 56 | 56 | 56 | 52.5 | 51 | 50.5 | 48.5 | 45.5 | 44.5 | 43.5 | 40.5 | 40 | 25 | 25 | 25 | 25 | 25
Ideal Burndown | 56 | 52.5 | 49 | 45.5 | 42 | 38.5 | 35 | 31.5 | 28 | 24.5 | 21 | 17.5 | 14 | 10.5 | 7 | 3.5 | 0