## Sheet1
Level 1 | Level 2 | Level 3 Work Packages | Level 4 Estimations | Actuals
1 Overview of ISO/IEC/IEEE 12207 | 1.1 WBS | 1.1.1 Group Meeting and Starting Template | 3 hours | 1
|  | 1.1.2 Identify Main Objectives | 2 hours
|  | 1.1.3 Create Sub-Objects and Complete Table | 3 hours | 0.5
|  | 1.1.4 Select Research Documents | 1 hour | 2
| 1.2 Project Plan | 1.2.1 Organize Objectives | 3 hours | 0.5
|  | 1.2.2 Distribute objectives amongst team members | 2 hours | 0.5
| 1.3 Research and Summarize | 1.3.1 Research and Identify Sources | 2 hours | 4
|  | 1.3.2 Split Sources and Read | 8 hours | *4
|  | 1.3.3 Create Outline for Research Paper Content | 1 hour
|  | 1.3.4 Summarize Our Research | 4 hours