## Slide 1: Status Report (S03)
Team 9: Daniel Park, Brenden Pace, Alexander Lundin, Jairo Galarza
SE 4381.501
03/28/2018

## Slide 2: Status
We have 8 hours of earned value this week
  We are categorizing earned value as the summation of estimated costs for every work package completed this week.
We saved 4.5 hours of value this week
  Some of the packages actually took less time than anticipated
  The next slide identifies this weeks work with ->
More work is tasked to individuals so we can summarize research this weekend
Notes: -> then transfer to next slide where we talk about it.

## Slide 3: WBS compared to actuals
Level 1 | Level 2 | Level 3 Work Packages | Level 4 Estimations |  | Actuals
1 Overview of ISO/IEC/IEEE 12207 | 1.1 WBS | 1.1.1 Group Meeting and Starting Template | 3 hours |  | 1
1.1.2 Identify Main Objectives | 2 hours |  | 2
1.1.3 Create Sub-Objectives and Complete Table | 3 hours |  | ->0.5
1.1.4 Select Research Documents | 1 hour |  | 2
1.2 Project Plan | 1.2.1 Organize Objectives | 3 hours |  | ->0.5
1.2.2 Distribute objectives | 2 hours |  | ->0.5
1.3 Research and Summarize | 1.3.1 Research and Identify Sources | 2 hours |  | 4
1.3.2 Split Sources and Read | 8 hours |  | ->4*
1.3.3 Create Outline for Research Paper Content | 1 hour |  | 
1.3.4 Summarize Our Research | 4 hours |  | 
Notes: -> then transfer to next slide where we talk about it.

## Slide 4: EV, PV, AC
Cumulative | Week 1 (2.26) | Week 2 (3.4) | Week 3 (3.11) | Week 4 (3.18) | Week 5 (3.25)
PV | 3 | 8 | 13 | 21 | 33
AC | 3.5 | 5.5 | 6.5 | 10.5 | 14.5
EV | 8 | 8 | 13 | 15 | 23
What this tells us is that we are overestimating the cost of the different objectives. This should not be a surprise as we were clueless on many of the tasks. We also projected that we would have done a bit more work in time by this point. This could correlate to the fact that we have a lot more done in the objective category.

## Slide 5: Risk Status
Risks
Information
  Conflicting source information.
  Not enough source information. (High Concern)
Personel
  Presenter becomes ill on presenting day.
  Team member becomes unable to work
  Possible lack of transparency
Workload
  Work packages that take longer than estimated.
Status
Information
  Our sources have not really have conflicted with each other that much.
  Collected 9 sources and summarized them.
Personel
  Pass the ball presentation style, anyone will be able to step in
  We have planned to cover for each other and are familiar with all the information that each team member has gathered
  Created Team Rules document and that we all signed
Workload
  Some work packages took less time to complete than expected, offsetting the packages that took longer than estimated to complete.